## Sheet1
Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 6) | Week #1 | Week #2 | Week #3 | Week #4 | Week #5 | Week #6 | Week #7 | Week #8 | Week #9
|  |  | 3/2 - 3/6 | 3/9 - 3/13 | 3/16 - 3/20 | 3/23 - 3/27 | 4/6 - 4/10 | 4/13 - 4/17 | 4/20 - 4/24 | 4/27 - 5/1 | 5/4 - 5/8
|  |  | 360 | 320 | 280 | 240 | 200 | 160 | 120 | 80 | 40 | Ideal Burndown
|  | 360 | 360 | 316 | 285 | 241 | 219 | 157 | 111 | 52 | 30 | Remaining Hrs (Total)
Research of 4 car rent web and brainstorm | Everyone | 20 | Week #1: 20
Project architecture and Assign tasks to each member | Everyone | 10 | Week #1: 8; Week #2: 2
Design Business Logic & User Story | Qin Wang & Chen Zhang | 10 | Week #1: 6; Week #2: 2; Week #4: 1; Week #6: 1
Finish UML Diagram | Yakun Feng | 10 | Week #2: 10
Review User Story & UML Diagram | Everyone | 10 | Week #3: 10
Project approach decision | Everyone | 10 | Week #1: 3; Week #2: 3; Week #3: 4
ERD & Schema For Database | Yakun Feng & Qin Wang | 20 | Week #2: 10; Week #3: 10
Review and modify of ERD & Schema | Everyone | 10 | Week #3: 10
Design User Interface | Chen Zhang & Qin Wang | 10 | Week #3: 8; Week #4: 2
Review and modify of User Interface | Everyone | 10 | Week #4: 5; Week #5: 5
Create Database | Yakun Feng | 20 | Week #4: 5; Week #5: 15
Implement Front-End Code | Qin Wang& Chen Zhang&Yakun Feng | 40 | Week #4: 5; Week #5: 30; Week #6: 5
Implement Back-End Code | Zhengyu Duan & Yakun Feng | 40 | Week #4: 2; Week #5: 10; Week #6: 18; Week #7: 10
Complete Unit Testing | Zhengyu Duan | 10 | Week #6: 8; Week #7: 2
Connect of Front-End and Back-End | Qin Wang & Zhengyu Duan | 30 | Week #6: 10; Week #7: 20
Front-End & Back-End Connection Test | Everyone | 10 | Week #7: 10
User Testing | Everyone | 20 | Week #7: 5; Week #8: 10; Week #9: 5
Weekly Scrum meeting | Everyone | 10 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Write Documentation | Everyone | 10 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Documentation Organize | Everyone | 10 | Week #1: 3; Week #2: 2; Week #6: 2; Week #9: 3
Deploy to AWS in an Auto Scaled EC2 Cluster | Qin Wang & Zhengyu Duan | 20 | Week #7: 10; Week #8: 10
Test on AWS and DEMO Prepare | Everyone | 20 | Week #9: 20
Team:
Zhengyu Duan | 10 hours / Week
Chen Zhang | 10 hours / Week
Qin Wang | 10 hours / Week
Yakun Feng | 10 hours / Week
Total Available Hours During Sprint ( 9Weeks ) : | 360